## Dashboard
Emotorad Test Summary Dashboard
| Modules List | Feature Count | Total Cases | Pass | Fail | Not in scope | Pass % | Progress | Progress Bar | Sanity Suite | Build Version | 1.0.1
| Amigo App & Ebike | On-boarding & Profile creation | 9 | 9 | 0 | 0 | 100 | 100 |  | Regression Suite | Device used for Testing | Samsung Galaxy A14 5G & Version -13
|  | Home page | 16 | 16 | 0 | 0 |  | 100 |  |  | Total Test Case | 81
|  | Connectivity | 10 | 10 | 0 | 0 |  |  | #N/A |  | Total Executed | 81
|  | Maps | 12 | 12 | 0 | 0 |  |  | #N/A |  | Total Pending | 0
|  | Engineering modes | 10 | 10 | 0 | 0 |  |  | #N/A |  | Execution Progress % | 100
|  | Ride details ,Stats & History | 3 | 3 | 0 | 0 |  |  | #N/A
|  | Child mode | 5 | 5 | 0 | 0
|  | Smart Lock | 6 | 6 | 0 | 0
|  | Smart Speaker | 10 | 10 | 0 | 0
| Total | 9 | 81 | 81 | 0
| Total Bugs | 10
| High | 5
| Highest | 4
| Medium | 1

## Test Case Design & Execution Pr
Date | Testcase Design count | Total Count
2023-12-12 | 25 | 25
2023-12-13 | 35 | 60
2023-12-14 | 40 | 100
2023-12-15 | 56 | 156
2023-12-18 | 45 | 201
2023-12-19 | 45 | 246 |  |  | Design
2023-12-20 | 45 | 291 |  |  | Estimated | 500
2023-12-21 | 45 | 336 |  |  | Achieved | 516
2023-12-22 | 45 | 381
2023-12-26 | 45 | 426
2023-12-27 | 45 | 471
2023-12-28 | 45 | 516
2023-12-29 | 41 | 557
Date | Test Case Execution Count | Pass | Fail | Total Count
2024-01-02
2024-01-03
2024-01-04
2024-01-12 | 54 | 53 | 1 | 54
2024-02-06 |  | 76 | 0 | 76
2024-02-09 | 88 | 81 | 7 | 88
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04

## On-boarding &profile creation
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested On
Em_04 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | Check the user can able to get one time password while updating valid mobile number | User should have installed Amigo App from playstore/Appstore | 1. The user should launch the Amigo App 2.Check the user is able to Enter the mobile number in mobile number field text -box . 3. Checkthe user should click on the "send otp" button once mob is updated. 4.Check the user is able to able to get the OTP(one -time -password) as Mentioned time . | 1. The user should able to launch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_06 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | check the user can able to enter the otp in Enter otp text field box | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3.The user should click on the "send otp" button once mob is updated. 4.The user should get OTP(one -time -password) as mentioned time . 5. The user is able to enter the one -time password in otp text field box 6.The user is able to reach home launcher screen while otp is entered. | 1. The user should able to launch the Amigo app without any issues 2. The user is able to enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time . 5The user should be able to add one-time password and able to reach the Complete profile screen | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_08 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | check the user can able to click the resend OTP link | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2.Check the user is able to Enter the valid mobile number in mobile number field text -box . 3.The user should click on the "send otp" button once mob is updated. 4.The user should get OTP(one -time -password) as mentioned time . 5. The user is able to click the resend -otp while reaching the time limit. 6.The user get new otp while click the resend otp link. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5. Check the user can click on the Resend otp link while reaching the time limit. 6. Check the user can get otp by clicking the resend otp link. | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_11 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | check the user Can able to select gender category | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7. Check the user is able to select the gender option list (male , female and others ) | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6.The user is able to select the gender category without any issues . | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_12 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | Check the user can able to enter the bike nick name | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7. Check the user is able to enter the Bike Nick name | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6.The user able to enter the bike nick name without any issues. | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_13 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | Check the user Can able to enter the Bike VIN Number | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7. Check the user is able to enter the Bike VIN Number | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6.The user able to enter the bike VIN Number without any issues. | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_14 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & Functional | Check the user can able to select the E-bike colour | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7. Check the user is able to select the colour's from listed of colour list. | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6. The user is able to select the colour from colour's list . | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_15 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI & functional | Check the user Can able to upload the profile photo form android /ios phone | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7. check the user is able to upload the image form android/ios phone. | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6. The user should be able to upload images form android/ios phone . | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_16 | P0 | PRD02_EM CApp - Onboarding & Profile Creation | On -boarding page & profile creation | Profile creation | Profile | UI &Functional | Check the user can able to click the complete profile link | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1.check The user should launch the Amigo App 2.Check the user is able to Enter the Valid mobile number in mobile number field text -box . 3. check The user should click on the "send otp" button once mob is updated. 4. check The user should get OTP(one -time -password) as mentioned time . 5. Check The user is able to enter the one -time password in otp text field box 6. Check The user is able to reach Complete profile screen while otp is entered. 7.Check the user is able to link the complete profile link ,once mandatory field is updated. | 1. The user should able to luanch the Amigo app without any issues 2.The user able to enter Mobile number in mobile number field text -box without any issues. 3. The User should Able to click -on the "send Otp" button without any issues . 4.The user should get OTP(one -time -password) as mentioned time . 5.The user should be able to add one -time password and able to reach Complete profile screen launcher. 6. The user should be able to click the complete profile link once mandatory field is updated . | Working as expected | Pass |  | Karthikeyan K | 16/02/2024
Em_118
Em_119
Em_120
Em_121
Em_122
Em_123
Em_124
Em_125
Em_126
Em_127 | [10 empty] | Not tested cases -51
Em_128 | [10 empty] | Tested cases -66
Em_129 | [10 empty] | Total -117
Em_130
Em_131
Em_132 | [10 empty] | Pass -57
Em_133 | [10 empty] | Fail -9
Em_134
Em_135
Em_136
Em_137
Em_138
Em_139
Em_140
Em_141
Em_142

## Home page
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested By | Tested on
Em_H1 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the existing user is able to reach the home page,after entering otp | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send otp" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter a Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time . 5. The user should be able to reach the Home page, once it is updated. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H5 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check if the user can connect the Bluetooth from the connecting link on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send otp" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and able to reach home page . 5. Check the user can connect the Bluetooth from the connect link on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) and able to reach the home page 5. The user should be able to connect the Bluetooth from the connecting link on the home page without issues. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H6 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can see the connecting status after the Bluetooth connection | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send otp" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. 5. Check the user can see the connecting status after the Bluetooth connection | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user should see the connecting status after the Bluetooth connection without any issues. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H8 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check if the user can see the disconnecting status after Bluetooth disconnection. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. 5. Check if the user can see the disconnecting status after Bluetooth disconnection. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user can see the disconnecting status after Bluetooth disconnection. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H9 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can connect the Bluetooth from the connect device link on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. 5. Check the user can connect the Bluetooth from the connect device link on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user should connect the Bluetooth from the connect device link on the home page without any issues. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H14 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the Activity icon or navigation on the bottom navigation bar on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. 5. Check the user can click the Activity icon on the bottom navigation bar on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user click the Activity icon on the bottom navigation bar on the home page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H15 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the ride icon on the bottom navigation bar on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated. 5. Check the user can click the ride icon on the bottom navigation bar on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user click the ride icon on the bottom navigation bar on the home page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H25 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the users can click the ride dashboard in the more options menu | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can click the ride dashboard in more options menu | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user clicks the ride dashboard in the More Options menu | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H26 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the logout from the more options menu on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can click the logout from the more options menu on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user click the logout from the more options menu on the h ome page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H27 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click on the more options menu on the home page. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can click on the more options menu on the home page. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send Otp" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user clicks on the more options menu on the home page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H33 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can view your ride Statistics | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can view your ride Statistics | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user should be able to view your ride Statistics without any issues. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H44 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | check the user can click the connect & disconnect button on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. check the user can click the connect & disconnect button on the home page | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user should be able to click the connect & disconnect button on the home page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H48 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the start your goals link on the home page . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can click the start your goals link on the home page. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user should be able to click the start your goals link on the home page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H49 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the connect device link on the home page. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page. 5. Check the user can click the connect device link on the home page. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user should be able to click the connect device link on the home page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H72 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can view all the bottom navigation bar on the home page . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page 5. Check the user can view all the bottom navigation bars on the home page. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5.The user should be able to view all the bottom navigation bars on the home page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
Em_H75 | P0 | https://docs.google.com/document/d/1EEofcMO8LK-OUPDTMLUnDDz7FFL-wW9GAEqKil-kyXw/edit | Homepage - All States | Home page | Home | UI & Functional | Check the user can click the let's go button on the home screen. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. The user should launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can click on the "send OTP" button once the mob is updated. 4. Check the user can reach the home page once the OTP is updated and reach the home page 5. Check the user can click the let's go button on the home screen. | 1. The user should able to launch the Amigo app without any issues 2. The user can enter the Mobile number in the mobile number field text -box without any issues. 3. The User should able to click -on the "send OTP" button without any issues. 4.The user should get OTP(one -time -password) as mentioned time (120 seconds) & reach home page 5. The user should be able to click the let's go button on the home screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024

## Connectivity
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Pre-condition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EMC-14 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLe Connection | Connectivity | UI & Functional | Check the user can proceed to the next screen after clicking the get started button on the instruction page. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4. Check the user can proceed to the next screen after clicking the get started button on the instruction page. | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to proceed to the next screen after clicking the get started button on the instruction page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-15 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLe Connection | Connectivity | UI & Functional | Check the user can view the connectable devices(EM -bike & Smart accessories) on the click to connect screen. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4. Check the user can view the connectable devices(EM -bike & Smart accessories) on the click to connect screen. | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The usere should be able to view connectable devices(EM -bike & Smart accessories ) on the click-to-connect screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-17 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can click the EM-bikes & smart accessories on the click to connect screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4. Check the user can click the EM-bikes & smart accessories on the click-to-connect screen | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4. The user should be able to click the EM-bikes & smart accessories on the click-to-connect screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-18 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can get notification for enabling the location [(<Android 12) devices] | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4. Check if the user can get a notification for enabling the location [(<Android 12) devices] | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4. The user should be able to get a notification for enabling the location [(<Android 12) devices] | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-21 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can clicking the deny option on the notification message .[(<Android 12) devices] | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4.Check the user can clicking the deny option on the notification message .[(<Android 12) devices] | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to clicking the deny option on the notification message .[(<Android 12) devices] | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-38 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can click the Allow button on the notification message to enabling the bluetooth | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4. Check the user can click the Allow button on the notification message to enabling the bluetooth | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to click the Allow button on the notification message to enabling the bluetooth | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-39 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can click the deny button on the notification message to deny the Bluetooth,The user can't move | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4.Check the user can click the deny button on the notification message to deny the Bluetooth | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to click the deny button on the notification message to deny the Bluetooth | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-57 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can clicking the get started button to reach home page . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4.Check the user can clicking the get started button to reach home page . | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to clicking the get started button to reach home page . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-62 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can clicking the connect devices button on the home page . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4.Check the user can clicking the connect devices button for aming connection with EM-bike | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user should be able to clicking the connect devices button for aming connection with EM-bike | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMC-78 | P0 | https://docs.google.com/document/d/1bACIQzcXxs6kj4MN8uXWnxLZ-EGv_9nI16D_Ugykql0/edit | Connectivity | BLE Connection | Connectivity | UI & Functional | Check the user can click the cancel button to cancel the option | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check The user can launch the Amigo App 2. Check the user can Enter the mobile number in the mobile number field text -box. 3. Check the user can reach the mandatory profile page and update the details. 4.Check the user can click the cancel button to cancel the option | 1. The user should be able to launch the Amigo app 2. The user should be able to enter the mobile number in the mobile number text box 3. The user should be able to reach the mandatory profile page and update the details 4.The user Should be able to click the cancel button to cancel the option | Working as expected | Pass |  | Karthikeyan k | 16/02/2024

## Maps
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EMM_02 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the lets go button or Navigation button on the bottom navigation bar on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3. Check the user can click the lets go button on the bottom navigation bar on the home page | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3. The user should be able to click the lets go button on the bottom navigation bar on the home page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_10 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the home icon on the main map screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the home icon on the main map screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the home icon on the main map screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_11 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the work icon on the main map screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3. Check the user can click the work icon on the main map screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the work icon on the main map screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_12 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the restaurants icon on the main map screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the restaurants icon on the main map screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the restaurants icon on the main map screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_13 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the charging station icon on the main map screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the restaurants icon on the main map screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the charging station icon on the main map screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_31 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the home icon under quick access screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the home icon under quick access screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the home icon under quick access screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_32 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the work icon under quick access screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the work icon under quick access screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the work icon under quick access screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_33 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the more icon under quick access screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the more icon under quick access screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the more icon under quick access screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_68 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can set the work location after click work location option under quick access | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the activity icon 4.Check the user can set the work location after click work location option under quick access | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the activity icon . 4.The user should be able to set the work location after click work location option under quick access | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_80 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the select on map button under the set home address screen. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the activity icon 4.Check the user can click the select on map button under the set home address screen. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the activity icon . 4.The user should be able to click the select on map button under the set home address screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_90 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the done button under home address location. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the activity icon 4.Check the user can click the done button under home address location. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the activity icon . 4.The user should be able to click the done button under home address location. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMM_111 | P0 | https://drive.google.com/drive/folders/17_yEtSu-_sywUPV_b3QbuKxiJMFaN9jb | MAPS | Navigation | MAPS | Ui & functional | Check the user can click the back navigation button after set the work address location | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the activity icon 4.Check the user can click the back navigation button after set the work address location | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the activity icon . 4.The user should be able to click the back navigation button after set the work address location | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .

## Ride Details, Stats & History
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested On
EMR_03 | P0 | https://docs.google.com/document/d/1wwQfTSKt7HYDIfr2jc_BVfJv_8K3mbpJHthzTSzniMc/edit | Ride Details | Stats | Ride Details & History | UI &Functional | Check the user can click the Activity icon on the bottom navigation bar on the home page . | 1.Check the user can upadte the mobile number and able to reach the complete profile screen. 2.Check the user can complete the complete profile screen and can reach the home page 3.Check the user can click the Activity icon on the bottom navigation bar on the home page . | 1.The user should be able to upadte the mobile number and able to reach the complete profile screen. 2.The user should be able to complete the profile screen and can reach the home page 3.The user should be able to click the Activity icon on the bottom navigation bar on the home page . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMR_12 | P0 | https://docs.google.com/document/d/1wwQfTSKt7HYDIfr2jc_BVfJv_8K3mbpJHthzTSzniMc/edit | Ride Details | Stats | Ride Details & History | UI &Functional | Check the user can click the recent ride home card on the activity screen. | 1.Check the user can upadte the mobile number and able to reach the complete profile screen. 2.Check the user can complete the complete profile screen and can reach the home page 3.Check the user can click the Activity icon on the bottom navigation bar on the home page . | "1.The user should be able to upadte the mobile number and able to reach the complete profile screen. 2.The user should be able to complete the profile screen and can reach the home page 3.The user should be able to click the Activity icon on the bottom navigation bar on the home page ." | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMR_21 | P0 | https://docs.google.com/document/d/1wwQfTSKt7HYDIfr2jc_BVfJv_8K3mbpJHthzTSzniMc/edit | Ride Details | Stats | Ride Details & History | UI &Functional | Check the user can click the ride history on the ride history page. | 1.Check the user can upadte the mobile number and able to reach the complete profile screen. 2.Check the user can complete the complete profile screen and can reach the home page 3.Check the user can click the Activity icon on the bottom navigation bar on the home page . | 1.The user should be able to upadte the mobile number and able to reach the complete profile screen. 2.The user should be able to complete the profile screen and can reach the home page 3.The user should be able to click the Activity icon on the bottom navigation bar on the home page . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024

## Child mode
Test Case ID | Priority | PRD | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EMCM_01 | P0 | https://docs.google.com/document/d/1nbiPGESS5qe9zWqHdWTwoKghtRlPZ6L_STZGA0zIihc/edit | Child mode | UI & functional | Check the user can click the more options on the home page . | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . | 1.Check the user can launch the Amigo application 2.Check the user can complete the login -process and reach the home page. 3.Check the user can click on the more options on the top right corner on the home page. | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the login -process and able to reach the homepage. 3.The user should be able to click on the more options on the top right corner on the home page. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMCM_21 | P0 | https://docs.google.com/document/d/1nbiPGESS5qe9zWqHdWTwoKghtRlPZ6L_STZGA0zIihc/edit | Child mode | UI & functional | Check the user can toggle on/off on the child mode setting option . | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . | 1.Check the user can launch the Amigo application 2.Check the user can complete the login -process and reach the home page. 3.Check the user can click on the more options on the top right corner on the home page. 4.Check the user can able to click the child mode option under profile hamburger 5.Check the user can toggle on/off on the child mode setting option . | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the login -process and able to reach the homepage. 3.The user should be able to click on the more options 4.The user should be able to click the child mode option under profile hamburger 5.The user should be able to toggle on/off on the child mode setting option . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMCM_24 | P0 | https://docs.google.com/document/d/1nbiPGESS5qe9zWqHdWTwoKghtRlPZ6L_STZGA0zIihc/edit | Child mode | UI & functional | Check the user can able to set the speed limit . | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . | 1.Check the user can launch the Amigo application 2.Check the user can complete the login -process and reach the home page. 3.Check the user can click on the more options on the top right corner on the home page. 4.Check the user can able to click the child mode option under profile hamburger 5.Check the user can able to set the speed limit . | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the login -process and able to reach the homepage. 3.The user should be able to click on the more options 4.The user should be able to click the child mode option under profile hamburger 5.The user should be able to set the speed limit . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMCM_31 | P0 | https://docs.google.com/document/d/1nbiPGESS5qe9zWqHdWTwoKghtRlPZ6L_STZGA0zIihc/edit | Child mode | UI & functional | Check the user can able to click the forget your pin option under the enter your pin text box. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . | 1.Check the user can launch the Amigo application 2.Check the user can complete the login -process and reach the home page. 3.Check the user can click on the more options on the top right corner on the home page. 4.Check the user can able to click the child mode option under profile hamburger 5.Check the user can toggle ON the child mode setting 6.Check the user can able to clicks the apply button under the set speed limit box. 7.Check the user can able to click the forget your pin option under the enter your pin tex | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the login -process and able to reach the homepage. 3.The user should be able to click on the more options 4.The user should be able to click the child mode option under profile hamburger 5.The user should be able to turn on the toggle 6.The user should be able to clicks the apply button under the set speed limit box. 7.The user should be able to click the forget your pin option under the enter your pin text box. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMCM_36 | P0 | https://docs.google.com/document/d/1nbiPGESS5qe9zWqHdWTwoKghtRlPZ6L_STZGA0zIihc/edit | Child mode | UI & functional | Check the user can able to click on the send otp button on the forgot password screen. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . | 1.Check the user can launch the Amigo application 2.Check the user can complete the login -process and reach the home page. 3.Check the user can click on the more options on the top right corner on the home page. 4.Check the user can able to click the child mode option under profile hamburger 5.Check the user can toggle ON the child mode setting 6.Check the user can able to clicks the apply button under the set speed limit box. 7.Check the user can able to click the forget your pin option under the enter your pin text box. 8.Check the user can view the forgot password screen after clicking on the forgot your pin. 9.Check the user can able to click on the send otp button on the forgot password screen. | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the login -process and able to reach the homepage. 3.The user should be able to click on the more options 4.The user should be able to click the child mode option under profile hamburger 5.The user should be able to turn on the toggle 6.The user should be able to clicks the apply button under the set speed limit box. 7.The user should be able to click the forget your pin option under the enter your pin text box. 8.The user should be able to view the forgot password screen after clicking on the forgot your pin. 9.The user should be able to click on the send otp button on the forgot password screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024

## Hardware
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested By | Tested On
EMH_01 | P0 |  | Hardware & buttons | Bluetooth | Hardware | Hardware | Check the user can able to pair with Aimgo app while turn on the Bluetooth connection. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user is able to Enter the mobile number and click the send otp button 2. Check the user can able to update the otp and proceed to the next screen. 3.Check the user can able to pair the EM-bike on the instruction page while turn on the bluetooth and location on the mobile | 1.The user should be able to Enter the mobile number and click the send otp button 2.The user should be able to update the otp and proceed to the next screen. 3.The user should be able to pair the EM-bike on the instruction page while turn on the bluetooth and location on the mobile
EMH_02 | P0 |  | Hardware & buttons | Battery | Hardware | Hardware | Check the user can able to turn on the battery On the EM-bike . | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to insert the batery on the EM-bike. 2.Check the user can able to turn on the battery on the EM-Bike. | 1.The user should be able to insert the batery on the EM-bike. 2.The user should be able to turn on the battery on the EM-Bike.
EMH_03 | P0 |  | Hardware & buttons | Battery | Hardware | Hardware | Check the user can able turn off the battery on the EM-Bike . | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to insert the batery on the EM-bike. 2.Check the user can able to turn off the battery on the EM-Bike. | 1.The user should be able to insert the batery on the EM-bike. 2.The user should be able to turn off the battery on the EM-Bike.
EMH_04 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check if the user is able to Power ON the E-Bike using Display Power Button | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to turn on the power button on the EM bike | 1.The user should be able to turn on the power button on the EM bike
EMH_05 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check if the user is able to Power OFF the E-Bike using Display Power Button | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1. Check the user can able to turn off the power button on the EM-Bike . | 1.The user should be able to turn off the power button on the EM-Bike .
EMH_06 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the '+' Button of the display Works or Not | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to press Plus button on the EM-bike . | 1.The user should be able to press Plus button on the EM-bike .
EMH_07 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the '-' Button of the display Works or Not | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to press the Minus button on the EM-bike . | 1.The user should be able to press the Minus button on the EM-bike .
EMH_08 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the PAS value is Changing or not using '+' & '-' buttons of the display | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to change the PAS mode While pressing the Plus button on the EM-bike | 1.The user should be able to change the PAS mode While pressing the Plus button on the EM-bike
EMH_09 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check if the PAS value is Changing Using '+' & '-' buttons ( Both on App & Display) | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to increase the PAS mode while pressing the plus button on the EM-Bike | 1.The user should be able to increase the PAS mode while pressing the plus button on the EM-Bike
EMH_10 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check if the PAS value is visible both on app & Display | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the PAS value on the Display board on the EM-bike. | 1.The user should be able to view the PAS value on the Display board on the EM-bike.
EMH_12 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check if the user can view the correct PAS value on the display & App while user tries to change the PAS Value. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the correct PAS value on the display board while user pressing the Plus and minus button | 1.The user should be able to view the correct PAS value on the display board while user pressing the Plus and minus button on the EM-bike.
EMH_13 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the PAS value on The amigo app on the ride dashboard | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the PAS value on The amigo app on the ride dashboard | 1.The user should be able to view the PAS value on The amigo app on the ride dashboard
EMH_14 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the battery soc percentage on the display board on the EM-bike | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the battery soc percentage on the display board on the EM-bike | 1.Check the user can view the battery soc percentage on the display board on the EM-bike
EMH_15 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the battey r soc percentage on the Ride dashboard on the Amigo App. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the battery soc percentage on the Ride dashboard on the Amigo App. | 1.The user should be able to battery soc percentage on the Ride dashboard on the Amigo App.
EMH_17 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the speed(kmph) value on display board on the EM-BIke | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the speed(kmph) value on display board on the EM-BIke | 1.The user should be able to view the speed(kmph) value on display board on the EM-BIke
EMH_18 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the speed(kmph) value on ride dashboard on the Amigo App | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the speed(kmph) value on ride dashboard on the Amigo App | 1.The user should be able to view the speed(kmph) value on ride dashboard on the Amigo App
EMH_19 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the Odemeter value on display board on the EM-Bike | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the Odemeter value on display board on the EM-Bike | 1.The user should be able to view the Odemeter value on display board on the EM-Bike
EMH_20 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the odemeter value on ride dashboard on the Amigo App. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the odemeter value on ride dashboard on the Amigo App. | 1.The user should be able to view the odemeter value on ride dashboard on the Amigo App.
EMH_21 | P0 |  |  | Powerbutton | Hardware | Hardware | Check the user can view the default mode will be "Urban mode" on the EM-Bike. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the default mode will be "Urban mode" on the EM-Bike. | 1.The user should be able to view the default mode will be "Urban mode" on the EM-Bike.
EMH_22 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can able to change to walk mode by Hold - Pressing the Minus button of the Display | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to change the walk mode while pressing the mins button on the EM-bike | 1.The user should be able to change the walk mode while pressing the mins button on the EM-bike
EMH_23 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the (P-walk mode) indication symbol on display board while user change the EM-bike to walk mode | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the (P-walk mode) indication symbol on display board while user change the EM-bike to walk mode | 1.The user should be able to view the (P-walk mode) indication symbol on display board while user change the EM-bike to walk mode
EMH_24 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the speed upto 5kmph while EM-bike on the walk mode | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the speed upto 5kmph while EM-bike on the walk mode | 1.The user should be able to view the speed upto 5kmph while EM-bike on the walk mode
EMH_25 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can able to change the mode while pressing the brake from walk mode to urabn mode | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can able to change the mode while pressing the brake from walk mode to urabn mode | 1.The user should be able to able to change the mode while pressing the brake from walk mode to urabn mode
EMH_26 |  |  |  | Powerbutton | Hardware | Hardware | Check the user can view the walk mode updating on the ride dashboard on the Amigo app/ | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike .
EMH_27 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user Can able to change the cruise mode while pressing the '-' button and raising the throttle on the EM-bike. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user Can able to change the cruise mode while pressing the plus button and raising the throttle on the EM-bike. | 1.The user should be able to change the cruise mode while pressing the plus button and raising the throttle on the EM-bike.
EMH_28 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the can view the speed(kmph) while user change the default mode to cruise mode | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the can view the speed(kmph) while user change the default mode to cruise mode | 1.The user should be able to view the speed(kmph) while user change the default mode to cruise mode
EMH_29 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can apply the brake or throttle to change the mode from cruise mode to default mode | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can apply the brake or throttle to change the mode from cruise mode to default mode | 1.The user should be able to apply the brake or throttle to change the mode from cruise mode to default mode
EMH_30 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the cruise mode icon on the display board on the EM-bike | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the cruise mode icon on the display board on the EM-bike | 1.The user should be able to view the cruise mode icon on the display board on the EM-bike
EMH_31 | P0 |  | Hardware & buttons | Powerbutton | Hardware | Hardware | Check the user can view the cruise mode updating on the ride dashboard on the Amigo App. | "User should have installed Amigo App from playstore/Appstore." User should have valid phone number . User should have EM-bike . | 1.Check the user can view the cruise mode updating on the ride dashboard on the Amigo App. | 1.The user should be able to view the cruise mode updating on the ride dashboard on the Amigo App.
EMH_32 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can able to turn on the key on the EM -bike
EMH_33 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can able to turn off the key on the EM-Bike
EMH_34 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can able to turn on the EM-Bike without turn on the Key
EMH_35 |  |  | Hardware & buttons |  |  | Hardware | Check the user can able to turn on the Em-Bike without turn on the Battery
EMH_36 | P0 |  | Hardware & buttons |  |  | Hardware | Check if the user can able to turn on the Em-bike ,if Battery and Key was turn on
EMH_37 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can able to change the mode while pressing the power button
EMH_40 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can trun on the EM-bike while press and hold the power button on the EM-Bike
EMH_41 | P0 |  | Hardware & buttons |  |  | Hardware | Check the user can able to check the modes on the EM-Bike, while single press on the power button .
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons
Hardware & buttons

## Engineering modes
Test Case ID | Priority | PRD | Category/ module | Sub Module | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EME_02 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can click the garage screen on the bottom navigation bar on the home page | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the garage screen on the bottom navigation bar on the home page | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the garage screen on the bottom navigation bar on the home page | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_06 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can click the engineering mode button on the garage screen | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_32 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can drive up to 20kmph If the user selects Eco mode. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can drive up to 20kmph If the user selects Eco mode. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able to drive up to 20kmph If the user selects Eco mode. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_33 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can't use the throttle If the user selects the fitness mode. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can't use the throttle If the user selects the fitness mode. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be can't able to use the throttle If the user selects the fitness mode. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_36 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can click the Apply button under About eco mode . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can click the Apply button under About eco mode . | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able to click the Apply button under About eco mode . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_38 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can view the Apply button under About Fiteness mode . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can view the Apply button under About Fiteness mode . | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able view the Apply button under About Fiteness mode . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_39 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can click the Apply button under About Fiteness mode . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can click the Apply button under About Fiteness mode . | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able to click the Apply button under About Fiteness mode . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_42 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can click the Apply button under About urban mode . | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can click the Apply button under About urban mode . | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able to click the Apply button under About urban mode . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_45 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can change the engineering mode If the user is on ready to go state. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can change the engineering mode If the user is on ready to go state. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should be able to change the engineering mode If the user is on ready to go state. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EME_46 | P0 | https://docs.google.com/document/d/1gsMskmXVucEpNXTkTId3gXQK8COL6ocuUhaWDpMsYoc/edit | Engineering modes | Modes | Ride behavioural control -Engineering modes | UI& Fucntional | Check the user can't change the engineering mode If the user is in the move state. | User should have installed Amigo App from playstore/Appstore User should have valid phone number . | 1. Check the user can launch the application 2. Check the user can complete the sign-in process and can reach the home page 3.Check the user can click the engineering mode button on the garage screen 4.Check the user can't change the engineering mode If the user is in the move state. | 1. The user should launch the application 2. The user should be able to complete the sign-in process and able to reach the home page. 3.The user should be able to click the engineering mode button on the garage screen. 4.The user should can't able to change the engineering mode If the user is in the move state. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .
User should have installed Amigo App from playstore/Appstore User should have valid phone number .

## Smart lock
Test Case ID | Priority | PRD | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EML_02 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI &Functionals | Check the user can able to click on the smart locker image on the click to connect screen. | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. CheckThe user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can click the connect or connect device button on the home page. 4.Check the user can able to click on the get started button on the instruction page. 5.Check the user can able to click on the smart speakers image on the connecting screen. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click the connect or connect device button on the home page. 4.The user should be able to click on the get started button on the instruction page. 5.The user should be able to click on the smart speakers image on the connecting screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EML_04 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI &Functionals | Check the user can able to click on the smart locker image on the pairing screen. | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. Check the user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can click the connect or connect device button on the home page. 4.Check the user can able to click on the get started button on the instruction page. 5.Check the user can able to click on the smart speakers or smart lockers image on the connecting screen. 6.Check the user can view the smart locker image and name on the pairing screen 7.Check the user can able to click on the smart locker image on the pairing screen. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click the connect or connect device button on the home page. 4.The user should be able to click on the get started button on the instruction page. 5.The user should be able to click on the smart speakers image on the connecting screen. 6.The user should be able to view the smart locker image and name on the pairing screen. 7.The user should be able to click on the smart locker image on the pairing screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EML_22 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI &Functionals | Check the user can able to click on the lock image on the garage screen. | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. Check the user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can able to click on the smart lock icon on the smart accessories tab on the home page. 4.Check the user can view the lock image on the garage screen . 5.Check the user can able to click on the lock image on the garage screen. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click on the smart lock icon on the smart accessories tab on the home page. 4.The user should be able to view the lock image on the garage screen . 5.The user should be able to click on the lock image on the garage screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EML_27 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI &Functionals | Check the user can able to toggle on the proximity unlock . | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. Check the user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can able to click on the smart lock icon on the smart accessories tab on the home page. 4.Check the user can view the lock image on the garage screen . 5.Check the user can able to click on the lock image on the garage screen. 6.Check the user can able to toggle on the proximity unlock . | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click on the smart lock icon on the smart accessories tab on the home page. 4.The user should be able to view the lock image on the garage screen . 5.The user should be able to click on the lock image on the garage screen. 6.The user should be able to toggle on the proximity unlock . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EML_29 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI &Functionals | Check the user can able to select the manual and automatic option under proximity unlock. | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. Check the user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can able to click on the smart lock icon on the smart accessories tab on the home page. 4.Check the user can view the lock image on the garage screen . 5.Check the user can able to click on the lock image on the garage screen. 6.Check the user can view the manual and automation option after toggle on the proximity unlock. 7.Check the user can able to select the manual and automatic option under proximity unlock. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click on the smart lock icon on the smart accessories tab on the home page. 4.The user should be able to view the lock image on the garage screen . 5.The user should be able to click on the lock image on the garage screen. 6.The user should be able to view the manual and automation option after toggle on the proximity unlock. 7.The user should be able to select the manual and automatic option under proximity unlock. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EML_31 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit | Smart lock | UI | Check the user can your mobile enters the proximity range smart lock will automatically unlock. | 1.The User should have installed Amigo app 2.The User should have valid Phone number 3.The User should have EM-bike . 4.The user should have smart lock | 1. Check the user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can able to click on the smart lock icon on the smart accessories tab on the home page. 4.Check the user can view the lock image on the garage screen . 5.Check the user can able to click on the lock image on the garage screen. 6.Check the user can view the manual and automation option after toggle on the proximity unlock. 7.Check the user can able to select the automatic option under proximity unlock. 8.Check the user can your mobile enters the proximity range smart lock will automatically unlock. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click on the smart lock icon on the smart accessories tab on the home page. 4.The user should be able to view the lock image on the garage screen . 5.The user should be able to click on the lock image on the garage screen. 6.The user should be able to view the manual and automation option after toggle on the proximity unlock. 7.The user should be able to view the text after selecting the automatic under proximity unlock. 8.The smart lock wil automatically locked when user enters into the proximity range. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024

## Speaker
Test Case ID | Priority | PRD | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
EMS_03 | P0 | https://docs.google.com/document/d/164amU4gApKPiWmoZG_xsEe8G4bOJPxzxCz52oEOstfk/edit |  | UI &Functionals | Check the user can able to click on the get started button. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1.Check the user can launch the amigo application. 2.Check the user can complete the log-in process and reach the home page 3.Check the user can able to click on the connect device button on the hompage . 4.Check the user can view the let's connect screen and get started button. 5.Check the user can able to click on the get started button. | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the log-in process and reach the home page 3.The user should be able to click on the connect device button on the hompage . 4.The user should be able to view the let's connect screen and get started button. 5.The user should be able to click on the get started button. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_05 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to click on the smart speakers image on the connecting screen. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. CheckThe user can launch the amigo application 2. Check The user can complete the login process and reach the home page . 3.Check the user can click the connect or connect device button on the home page. 4.Check the user can able to click on the get started button on the instruction page. 5.Check the user can able to click on the smart speakers image on the connecting screen. | 1.The user should be able to launch the amigo application 2.The user should be able to complete the login process and reach the home page . 3.The user should be able to click the connect or connect device button on the home page. 4.The user should be able to click on the get started button on the instruction page. 5.The user should be able to click on the smart speakers image on the connecting screen. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_12 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to click on the proceed button on the instruction page . | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1.Check the user can launch the amigo application. 2.Check the user can complete the log-in process and reach the home page 3.Check the user can able to click on the connect device button on the hompage . 4.Check the user can view the let's connect screen and get started button. 5.Check the user can able to click on the get started button. 6.Check the user can click the speaker image for pairing . 7.Check the user can able to click on the proceed button on the instruction page . | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the log-in process and reach the home page 3.The user should be able to click on the connect device button on the hompage . 4.The user should be able to view the let's connect screen and get started button. 5.The user should be able to click on the get started button. 6.The user should be able to click the speaker image for pairing . 7.The user should be able to click on the proceed button on the instruction page . | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_13 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can re-direct to bluetooth setting page for connecting the bluetooth speaker | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1.Check the user can launch the amigo application. 2.Check the user can complete the log-in process and reach the home page 3.Check the user can able to click on the connect device button on the hompage . 4.Check the user can view the let's connect screen and get started button. 5.Check the user can able to click on the get started button. 6.Check the user can click the speaker image for pairing . 7.Check the user can able to click on the proceed button on the instruction page . 8.Check the user can re-direct to bluetooth setting page for connecting the bluetooth speaker | "1.The user should be able to launch the amigo application. 2.The user should be able to complete the log-in process and reach the home page 3.The user should be able to click on the connect device button on the hompage . 4.The user should be able to view the let's connect screen and get started button. 5.The user should be able to click on the get started button. 6.The user should be able to click the speaker image for pairing . 7.The user should be able to click on the proceed button on the instruction page ." 8.The user should be able to re-direct to bluetooth setting page for connecting the bluetooth speaker | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_14 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can hear the audio "“device successfully connected" once speaker successfully connected. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1.Check the user can launch the amigo application. 2.Check the user can complete the log-in process and reach the home page 3.Check the user can able to click on the connect device button on the hompage . 4.Check the user can view the let's connect screen and get started button. 5.Check the user can able to click on the get started button. 6.Check the user can click the speaker image for pairing . 7.Check the user can hear the audio "“device successfully connected" once speaker successfully connected. | 1.The user should be able to launch the amigo application. 2.The user should be able to complete the log-in process and reach the home page 3.The user should be able to click on the connect device button on the hompage . 4.The user should be able to view the let's connect screen and get started button. 5.The user should be able to click on the get started button. 6.The user should be able to click the speaker image for pairing . 7.The user should be able to hear the audio "“device successfully connected" once speaker successfully connected. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_15 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to press the play /pause button on the speakers | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. Check the user can able to turn on the speaker for pairing . 2.Check the user can view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.Check the user can able to press the play /pause button on the speakers | 1.The user should be able to turn on the speaker for pairing . 2.The user should be able to view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.The user should be able to press the play /pause button on the speakers | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_16 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to change the next music track while short pressing the + icon on the speaker | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. Check the user can able to turn on the speaker for pairing . 2.Check the user can view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.Check the user can able to change the next music track while short pressing the + icon on the speaker | 1.The user should be able to turn on the speaker for pairing . 2.The user should be able to view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.The user should be able to change the next music track while short pressing the + icon on the speaker | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_17 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to change the previous music track while short pressing the - icon on the speaker. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. Check the user can able to turn on the speaker for pairing . 2.Check the user can view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3. Check the user can able to change the previous music track while short pressing the - icon on the speaker. | 1.The user should be able to turn on the speaker for pairing . 2.The user should be able to view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.The user should be able to change the previous music track while short pressing the - icon on the speaker. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_19 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to end the call while Short press the play/pause button on the speaker | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. Check the user can able to turn on the speaker for pairing . 2.Check the user can view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.Check the user can able to end the call while Short press the play/pause button on the speaker | 1.The user should be able to turn on the speaker for pairing . 2.The user should be able to view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.The user should be able to end the call while Short press the play/pause button on the speaker | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
EMS_21 | P0 | https://docs.google.com/document/d/1GJu9m4uNm2Xghgmrcfv-YdZVKVQT1BbM8JGMML1VEN4/edit |  | UI &Functionals | Check the user can able to decrease the volume Long press the ‘-’ button on the speaker. | 1.User should have installed Amigo app 2.User should have valid Phone number 3. User should have EM-bike . 4.user should portable bluetooth speaker. | 1. Check the user can able to turn on the speaker for pairing . 2.Check the user can view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.Check the user can able to decrease the volume Long press the ‘-’ button on the speaker. | 1.The user should be able to turn on the speaker for pairing . 2.The user should be able to view the The LED on the speaker blinks in blue colour indicating that the speaker is in pairing mode 3.The user should be able to decrease the volume Long press the ‘-’ button on the speaker. | Working as expected | Pass |  | Karthikeyan k | 16/02/2024
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals
UI &Functionals

## Notification
Test Case ID | Priority | PRD | Component | Test Type | Test Objectives | Precondition | Test procedure | Expected Result | Actual Result | Status | Bug id | Tested by | Tested on
| P0 |  |  | UI |  |  | 1.Check the user can view the ""Bluetooth Pairing Failed" notification ,If Bluetooth pairing unsuccessful/error | 1.The user should be able to view the ""Bluetooth Pairing Failed" notification ,If Bluetooth pairing unsuccessful/error |  | Pass |  | Karthikeyan k | 2024-05-02
| P0 |  |  | UI | [5 empty] | Not tested
Not tested